# CO2301 Project Management

# Assignment Specification (70%)

Due on Friday 6th December 2024

I. 	Objective

The assignment develops the student's to acquire practical project management related skills when considering implementing a project.

- Important Dates:

| 1. Starting date | Friday 8th November 2024 @9:00am |
| --- | --- |
| 2. Submission deadline | Friday 6th December 2024 @12:00 pm |
| 3. Feedback date | 20 working days after submission due day |

- Policy on Plagiarism

  - The School operates the principle that both the plagiarised and the plagiariser are equally guilty. Students are therefore responsible for ensuring that their work is not plagiarised, and note that this includes ensuring that any work stored on the departmental and/or university computer systems is suitably protected.

  - Note that the school reserves the right to exact any penalties which are in accordance with the University's code of practice on plagiarism.

  - The School has its own set of regulations concerning plagiarism. The Department takes this issue very seriously, and students should note that on occasions in the past some very serious penalties have indeed been applied, including reduction of module mark to zero, and overall reduction of degree class.

  - Additionally: Plagiarizing any part of the assignment will result in getting a ZERO in the whole assignment.

- Assignment

Your assignment is to research and define a project for a City Hospital Patient Booking system. The project is based over a 30-month period. You should prepare the following:

- A Work Breakdown Structure (see additional notes 1.)

- Produce a Budget for Resources (see additional notes 2.)

- Prepare a Risk Register for the system (see additional notes 3.)

- Identify the Critical Path for a project (see additional notes 4.)

Please note the following information:

- Work Breakdown Structure:

- In addition to your WBS, you should include a list of all tasks to be performed within the project in the form of work packages.

- For each sub-task (Work Package), assign a project role responsibility. You may use some of the roles allocated to the project below.

(2) Budget for Resources:

Staff costs

- 1 x Project Manager, salary £85,000 per annum. Seconded to the project on an 80% basis

- 3 x Applications Architect, salary £60,000 per annum. Seconded to the project on a full-time basis.

- 4 x Cloud/Software Applications Engineers, both salaries £50,000 per annum. Seconded to the project on a full-time.

- 1 x Quality Assurance Tester, salary £60,000. Seconded to the project on a 75% basis.

- 2 x IT Training Consultant, salary £40,000 per annum. Seconded to the project on a 50% basis.

Technical equipment

- Cloud Server: 		£50,000

- Web Server:	 		£39,000

- Database Server:		£45,000

- 10 x Desktop computers:	£895.00 each

Software

- 10 x Licenses £6,500 each

(3) Risk Register:

Produce a risk register based on the city hospital project above.

- Your risk register should contain at a minimum of ten risks

- Your risk register should include at least three different types of risks.

- Your risk register should include an appropriate individual who is responsible for managing the risk.

- For each risk explain show the likelihood and impact.

(4) Critical Path Analysis:

Using information from the table below:

- Construct a project network

- Perform forward and backward passes

- Determine the project completion time

- Calculate slack values

- State the critical path

| Activity | A | B | C | D | E | F | G |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Immediate Predecessor | - | - | A | A, B | D | C, E | F |
| Expected Time (Weeks) | 9 | 14 | 13 | 9 | 10 | 7 | 8 |

Marking Criteria

| Criteria | Weighting | 0% - 5% | 6% - 10% | 11% - 15% |
| --- | --- | --- | --- | --- |
| Work Breakdown Structure | 15% | None or little attempt to producing a meaningful structure. | A good attempt to producing a meaningful structure. | A very good attempt to producing a meaningful structure. Work packages appropriately assigned to a project team role. |
| Budget for Resources | 15% | None or little attempt at preparing a budget. | A good attempt at preparing a budget, with some errors. | A very good attempt at preparing a budget, with minor errors. |
| Risk Register | 15% | None or little attempt at producing a risk register. | A good attempt at producing a risk register. | A very good attempt at producing a risk register. |
| Critical Path Analysis | 15% | None or little attempt at preparing network diagram, containing forward and backward values, slack and critical path | A good attempt at preparing network diagram, containing forward and backward values, slack and critical path. Some of the values and information are incorrect. | A very good attempt at preparing network diagram, containing forward and backward values, slack and critical path. Most or all the me of the values and information are correct. |
| Criteria | Weighting | 0% - 0.5% | 1% |  |
| Submit-1: Weekly Lab Activity worth 1% x 10 weeks | 10% | None or a few lab activities submitted with little evidence of work carried out. | All lab activities submitted with evidence of some/all work carried out. |  |
| Total | 70% |  |  |  |

Assignments will ONLY be accepted via Blackboard Turnitin

_____________________________________________

End of paper